## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-2-therightangle
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket.
Donate Money: As a helper, I want to send money so that a need gets met | Given that i am not on the u-fund site when i'm not on the Donations page then i must see a means to navigate to the Donations page
Given I want to donate when I click the checkout button then I EXPECT to see a success or failure screen.
Log in: As either a Manager or a Helper, I want to keep my payment information and management privileges exclusive to myself so that attackers can’t disrupt or steal donations. | Given I am on the log in screen when I type in my username and password then I EXPECT to see my home page.
Register for account: As either a Manager or a Helper, I want to create an account so that my payment information is private. | Given I don't have an account when register then I expect to see my account.
Donate time: As a Helper, I want to volunteer my time so that a need gets met. | Given I want to donate time when I click the donate time button then I expect my time slot.
Given that i am not on the u-fund site when i'm not on the Donations page then i must see a means to navigate to the Donations page
Configure payment destination: As a Manager, I want to control where donations go so that I can stay organized. | Given I'm on the needs detail when I click the set payment destination then I expect to see a success/failure screen.
Edit needs as manager: As a Manager, I want to change the order of needs as well as the deadline, required dollar amount, collected total, and volunteer opportunities for each need so that needs can be kept up to date if something happens. | Given I'm on the need details when I click update then I EXPECT to change the need details.
Remove needs: As a Manager, I want to decide when a need is removed so that I control when a need is no longer necessary. | Given I'm on need details when the manager click delete then I EXPECT to see the need get deleted.
Add/remove a need to funding basket: As a Helper I want to add and remove needs from my funding basket so that I can choose what to fund. | Given when I see the needs when click the add/remove needs button then I EXPECT the corresponding action to happen to the funding basket.
Dashboard: As a developer, manager, or helper, I want to see everything I’m supposed to see on my screen so that I can use this website. | Given I set my username to admin when I log in then I EXPECT to be a Manager, not a Helper.
Set permissions: As a Manager, I want to manage permissions of Helpers so that sensitive information is hidden from strangers. | Given that I am on the u-fund site when I am not on the Perms page where perms can be managed, then I must see a means to navigate to said page.
Given that I am not on the Perms page when I choose the Perms page then I am taken to the Perms page.
Given that I am on the Perms page after i've changed a perm I should see a message indicating that it has been altered
Set need visibility: As a Manager I want to make some needs visible only to authorized volunteers so that I can hide personal information from strangers. | Given a Manager selects the visibility option for a need, then it should only become visible to volunteers of the Managers choosing
Given that a Manager is logged into the system, when they access the needs management interface, then they should only see options to mark each need as visible to trusted volunteers
When a volunteer attempts to access the list of needs, then they should only see the needs that the Manager has made visible
View list of progress time stamps: As a Manager I want to see progress entries for a need so that I am better informed. | Given i'm a Manager, then I should be able to access a list of progress entries for a specific need.
Given a Manager views a list of entries then they should be able to see when (time and day) an entry was recorded
**Given** the page _thinks_ I'm an admin **when** I see need details **then** I expected to see transactions
As a developer I want to keep track of progress time stamps for a Need so that other functionality can be established. | **Given** I have made a payment **when** I checkout **then** I EXPECT the timestamp at which I made the payment to be added to the backend.
CSS: As a user I want to see a visually effective website so that I can use the site more effectively. | **Given** I am a mildly critical person **when** I am looking at any part of the website **then** I EXPECT to not hate the website layout.